## Slide 1: Aerospace Support to the Decadal Study Large Mission Concept Teams
Debra L. Emmons, PhD.
Principal Director
NASA Science & Technology Programs
24-25 April 2017
Presentation to NASA Astrophysics Advisory Committee (APAC)

## Slide 2: Agenda
Cost and Technical Evaluation (CATE) Background
Support to the Decadal Study Large Mission Concept Teams
Considerations for Design Trades

## Slide 3: What is a CATE?: Cost and Technical Evaluation
CATE developed by NAS/Aerospace for recent Decadal Surveys
  Previous Decadal Surveys had no process to validate advocate mission costs
  US Congress required National Academies to use independently validated costs
  CATE estimates needed to reflect historical project growth
    CATE estimates needed to reflect realistic NASA/ESA cost sharing
    Realistic CATE estimates needed for future budget analysis & decisions
CATE process differs from typical ICE and process for TMC evaluation
  Begins with typical Independent Cost Estimate, ICE
  Adds three types of cost threats, where appropriate:
    Schedule, design (mass & power growth) and launch vehicle
CATE is used for future consideration with respect to NASA budgets
  Used to evaluate science value versus budget availability
    Sometimes used to re-assess Decadal recommended concept descopes
  Incorporates typical growth based on the historical record and design maturity
    It is more conservative than an ICE of a “specific” concept presented

## Slide 4: Aerospace is the Custodian for the NAS CATE Process
Requires independent analysis
  Reconciliation with Project teams is recommended, where appropriate
  However, NAS committees are concerned with maintaining confidentiality
Requires consistency across diverse concepts
  CATE process is flexible to handle differences in design maturity
  CATE has been used for Astro2010, Planetary and Heliophysics
    Will be used for Earth Science Decadal in 2016
    May be used for Astro2020 and beyond
Stay true to the NAS process
  Advocate teams and NASA HQ do have special requests
  This often can be handled, but the CATE generated S-curve represents the cost risk assessment
  There is a “T” in CATE and committees and decision makers need a consistent technical risk assessment

## Slide 5: General Limitations of Assessment
Technical risk assessment
  Limited to top-level maturity and risk discussions
    Not meant to be a Proposal Evaluation level of effort
Cost and schedule assessment
  Meant for high-level budgetary estimates
    Often includes a profile in real year dollars
  It is understood that the CATE is likely to be higher than advocate estimate
    Decision makers consider the range in the two estimates
  When appropriate, reconciliation with the project occurs
    Typically when CATE is being presented to NASA HQ
    Does not occur when under direct evaluation by an NAS committee
  Design growth threat is typically the biggest disconnect with project teams
    Project often defends specific concept being presented
    Advocate estimate may not adequately factor in “future” modifications and “growth”

## Slide 6: Technical Risk & Maturity Assessment Approach
Identify key risks to achieving required performance
  Highlight significant deviations from current state of the art performance
  Trace performance risk to science mission impact
  Evaluate potential of planned risk mitigation efforts
Assess technical maturity risk liens on cost and schedule
  Assess claimed TRL level of key technologies
  Apply mass and power growth contingencies consistent with maturity
    Mass growth allowance could result in launch vehicle cost threat
  Late technology maturation steps identified as schedule risks
  Complex system integration issues identified as schedule risks
Low | Medium Low | Medium | Medium High | High

## Slide 7: Project X Top Technical Risks and Concerns
Medium new development, mostly in the engineering implementation
  Increase in detector array size
  Migration from FPGAs to ASICs
  Modernization of heritage instrument control unit
Mass margins and power margins are aggressive and launch mass margin is very sensitive to changes in dry mass
  Concept design is closer than recommended to Atlas V 551 capacity limit and the system is very sensitive to changes in mass
  Several mass liens against concept design
Time critical mission operations contributes to medium operational risk
  Fault management for autonomous mode requires further definition
  Sampling operations and hardware need further definition
Project X Technical Risk Rating is Medium
Example Only

## Slide 8: CATE Cost Estimating Approach Overview
Estimate Instruments & Spacecraft
Multiple analogies and models
Estimate Other Elements
Based on historical data
Estimate Cost Reserves
Based on probabilistic cost risk analysis
Estimate Mass and Power Contingency Threat
Re-run estimate with Aerospace contingencies
Estimate Schedule Threat
Based on ISE results and project burn rates
Integrate Results & Level Across Concepts
Cross-check with CoBRA

## Slide 9: Example Hardware Estimate Results
Chart: Estimated Cost (FY15$M)
| Project | Aero | Model 1 | Model 2 | Analogy 1 | Analogy 2 | Analogy 3 | Analogy 4
Project | 97
Aerospace | 105
Model | 110.8526 | 93
Adjusted Analogy | 117.6041 | 130.3288 | 71.5621 | 110.575
Notional Results

## Slide 10: Cost Risk Process Overview
Total Distribution is a Combination of Cost Distributions for WBS Elements
Multiple Cost Estimates for Each WBS Element
Example Total Cost Distribution
+
+
WBS Element 1
Total Cost Probability Distribution
WBS Element 2
. . .
Lower Limit
Most-Likely
Probability
Cost
Triangular Distribution of Possible Element Cost
L
M
H
+
WBS Element N
70th Percentile
Initial Cost Reserves Estimate
Sum of Most-likely Costs
DMF
DMF: Design Maturity Factor added to high estimate to capture worst case
Upper Limit
H
L
M
Used to estimate reserves

## Slide 11: Design Growth and Launch Vehicle Threats
All CATE estimates based on project team inputs
  Wide range in the maturity of the designs
  Some responses are essentially concept descriptions
  Others already have had significant investment maturing the design and required technology
Need to ensure that immature projects didn’t have an unfair advantage
  Apply higher mass and power contingencies for less mature projects
    Mass and power drive cost estimates from both analogies and models
  Use project-supplied contingencies for estimate without threats
Aerospace-applied contingencies to develop “Design Growth” cost threat
Add cost of moving to next larger launch vehicle as “Launch Vehicle” cost threat
  If mass contingency results in less than 10% launch vehicle mass margin

## Slide 12: Payload Mass Contingency Values for Threat Estimate
CATE contingency values are an extrapolation of historical Astrophysics mission data
Used for
Astrophysics CATEs
Actual Past Mission
Contingency

## Slide 13: Example Cost Estimate Table
Notional Results

## Slide 14: CATE Conclusions
CATE is a consistent and robust process to estimate missions for prioritization within a budget constraint profile
  Analogies and parametric models are used
  Instruments and spacecraft are key drivers and often are under estimated by the projects
  Process uses a statistical approach to capture appropriate reserves
    Concept maturity
    Technology readiness
  Process uses historical data to address likely cost threats
    Design growth
    Schedule
    Potential change in launch vehicle
Results are suitable for prioritization and long-range planning
CATEs will be incorporated into future NRC Decadal Surveys

## Slide 15: Objectives for Support to Large Mission Concept Teams
Prime objective
  Achieve a better understanding of technical, cost-risk trades and the impacts on the large concepts
Approach for achieving the prime objective
  Help study teams to understand cost and risk implications of their mission architecture choices
  Help study teams to better distinguish between areas for deeper engineering and areas where rules of thumb can suffice
  Aerospace Corporation to provide independent guidance and suggestions to the study teams for consideration in reducing the technical and cost risk of the engineering elements.
  Allow Aerospace to better understand mission concepts, technology requirements and technology maturity as the studies progress, without commenting on the science merits and without creating a conflict of interest situation with National Academies

## Slide 16: NASA Guidance to the Astrophysics Large Mission Concept Teams
Every team will have an ‘allowance’ of 400 work hours plus $4.5K of travel support from The Aerospace Corporation for their mission concept studies
  This support is from March 8, 2017 through December 31, 2018
  This includes Phase 1 and 2 support only (in-scope items from Task statement on next slide)
  This allocation does not include the costing and full CATE-like support (this is Phase 3 support for APD) and is not within scope of this effort
Each team can prioritize the in-scope Phase 2 (next slide) support from Aerospace
Teams have the option of using their own study funds to augment this support
Phase 1 of the original task, which included education to the teams on the CATE process is considered complete.
A CATE will be accomplished for each mission concept for the Astrophysics Division, but will be performed after the final reports are submitted to the Division and is not included in this effort; CATE is considered Phase 3 support
On the next page is a menu of tasks that are in scope that can be prioritized by each team
Notes: Aerospace will conduct an “initial observations” activity to provide an initial assessment of cost risk
Initial observations briefing will consist of:
  Summary of our understanding of the concept
  Assessment relative to available launch vehicles
  Top technical risks and concerns
  Other potential risks and concerns
  Cost considerations/recommendations
  Comments on project’s own cost estimate (if available)
  Remaining challenges
  Recommendations on how to potentially address risks or other challenges
Followed by more comprehensive “red team review” in Aug/Sep 2017 after concepts are closer to being finalized

## Slide 17: NASA Guidance – In Scope Tasks
Phase 2 – Trade Study Support
  Feedback on concepts and mission architecture choices
    Includes consultation of IDL/MDL runs
    Identification of risks
  Feedback on technology roadmaps
    Includes identification of gaps and risks
  Support of F2F meetings as determined by team leadership
  Review interim and final reports
  Note: Additional tasks that are not included in the above menu, but were submitted in the team’s request for support, can be conducted using these allocated hours, if the teams end up not using all of the allocation. However these must be negotiated with the DSMT before proceeding

## Slide 18: Aerospace Support Provided in Phase I
Cost and Risk Coaching (at Key decision Points and/or to inform key trades)
Independent Technology readiness level assessment
Margin Guidance
Discuss the CATE at the PAL and November F2F meetings
F2F meetings and presentations
  Pause & Learn Meeting at HQ – October 20th (Bob Bitten/Angie Bukley)
  Aerospace Briefing on CATE process -- November F2F
    Lynx (X-Ray Surveyor) F2F - Washington DC on 14-15 November
    OST F2F – Boulder, CO on 2-3 November
    LUVOIR and HabEx F2Fs the week of 09-11 November in New Haven, CT
On-call support to the Instrument and Mission Design Lab runs

## Slide 19: Considerations for Trades & Costing
Launch Vehicle
  May want to look at trade of maximizing science on existing launch vehicles as well as trades beyond current state of the art vehicles
On-orbit Servicing
  Development cost of including provisions for on-orbit servicing will be part of cost of mission
  Cost of future operational servicing would be outside of budget
International Partners
  Missions will be costed as a complete project and elements will be subtracted as international partnership is acknowledged